## Settings
NextID | Status | Assignee | TaskGroup | Holidays
20 | Not Started | me | Ob1 - Objective 1 | 2023-03-05
| In Progress - On Track |  | Ob2 - Objective 2 | 2023-03-06
| In Progress - At Risk |  | Ob3 - Objective 3 | 2023-03-07
| Blocked |  | Project | 2023-03-08
| Completed |  | Paper | 2023-03-09
|  |  | Presentation | 2023-03-10
|  |  | Forward Example | 2023-03-11
|  |  | Backward Example | 2023-03-12
2023-05-29
2023-06-19
2023-07-04
2023-07-24
2023-09-04
2023-10-08
2023-10-09
2023-10-10
2023-10-11
2023-10-12
2023-10-13
2023-10-14
2023-10-15
2023-11-23
2023-11-24
2023-11-25
2023-11-26
2023-12-24
2023-12-25
2024-01-01
2024-01-15
2024-02-19
2024-03-03
2024-03-04
2024-03-05
2024-03-06
2024-03-07
2024-03-08
2024-03-09
2024-03-10
2024-05-27
2024-06-19
2024-07-04
2024-07-24

## TasksGantt
Project Summary Information
Overall start: |  | 2023-02-15
Overall end: |  | 2023-03-27
Filtered start: |  | 2023-02-15
Filtered end: |  | 2023-03-27
Overall work days: |  | 24
Overall calendar days: |  | 40
Filtered work days: |  | 24
Filtered calendar days: |  | 41
Today:
Planned work:
Actual work:
Next ID #: |  | 20
Date: | time axis 2023-02-15 to 2024-03-20
ID | Task Short Description | Task Notes | Task Group | Assignee | Due Date | Status | Percent Complete | Independent Start Date | Independent End Date | Dependency ID | Dependency Type | Dependency Lag Days | Planned Workdays | Planned Start | Planned End | Actual Start | Actual End | Actual Workdays | time axis 2023-02-15 to 2024-03-20
1 | Forward one | Start from the beginning of the project. | Forward Example |  |  | In Progress - At Risk | 90% | 2023-03-14 |  |  |  |  | 2 | 2023-03-14 | 2023-03-15
2 | Forward two |  | Forward Example |  | 2023-03-23 | Blocked | 10% |  |  | 1 | FS | 1 | 3 | 2023-03-17 | 2023-03-21
3 | Forward three |  | Forward Example |  |  | Not Started |  |  |  | 2 | FS |  | 4 | 2023-03-22 | 2023-03-27
4 | Backward one | Start from the end of the project. | Backward Example | [5 empty] | 2023-03-14 |  |  |  | 2 | 2023-03-13 | 2023-03-14
5 | Backward two |  | Backward Example | [6 empty] | 4 | SF |  | 3 | 2023-03-01 | 2023-03-03
6 | Backward three |  | Backward Example |  |  | In Progress - On Track | 50% |  |  | 5 | SF |  | 4 | 2023-02-23 | 2023-02-28
7 | Backward four |  | Backward Example |  |  | Completed | 100% |  |  | 6 | SF | -1 | 5 | 2023-02-15 | 2023-02-21 | 2023-02-16 | 2023-02-22 | 5
8 | test 1 |  | Presentation |  |  | In Progress - On Track | 10% | 2023-03-14 |  |  | FS |  | 10 | 2023-03-14 | 2023-03-27
9 | Backward four
10
11
12
13
14
15
16 | text
17 | text
18 | text
19 | text
Note on M19: Christopher Macintosh: There are four dependency types available. The first letter in the dependency type codes refers to the other task. The second letter refers to this task. Available Dependency Types: FS - Finish-to-Start (Forward) [Other task finishes before this task starts.] SS - Start-to-Start (Forward) [Both tasks start at the same time.] SF - Start-to-Finish (Backward) [Other task starts after this task finishes.] FF - Finish-to-Finish (Backward) [Both tasks finish at the same time.]
Note on N19: Christopher Macintosh: The dependency lag allows you change the start time of the next task. Positive numbers will push the start date further into the future. Negative numbers will move the start date in the opposite direction. Example: 1 - delays the start date by one day -1 - moves the start day one day sooner

## WBS-Wide
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Alt Text | ID | Name | Next Step ID | Connector Label | Shape Type | Alt Text
P100 | Parent process | P200,P300,P400 | one,two,three | Process |  | 0 | Project Name | 1,2
P200 | Level 1 process | P500,P600 |  | Process |  | 1 | Level 1 Item | 1.1,1.2
P300 | Level 1 process | P700,P800 |  | Process |  | 1.1 | Level 2 Item | 1.1.1
P400 | Level 1 process | P900 |  | Process |  | 1.1.1 | Level 3 Item
P500 | Level 2 process |  |  | Process |  | 1.2 | Level 2 Item | 1.2.1
P600 | Level 2 process |  |  | Process |  | 1.2.1 | Level 3 Item
P700 | Level 2 process |  |  | Process |  | 2 | Level 1 Item | 2.1,2.2
P800 | Level 2 process |  |  | Process |  | 2.1 | Level 2 Item | 2.1.1
P900 | Level 2 process |  |  | Process |  | 2.1.1 | Level 3 Item
[6 empty] | 2.2 | Level 2 Item | 2.2.1
[6 empty] | 2.2.1 | Level 3 Item
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Alt Text
P100 | Parent process | P200,P300,P400 | one,two,three | Process
P200 | Level 1 process | P500,P600 |  | Process
P300 | Level 1 process | P700,P800 |  | Process
P400 | Level 1 process | P900 |  | Process
P500 | Level 2 process |  |  | Process
P600 | Level 2 process |  |  | Process
P700 | Level 2 process |  |  | Process
P800 | Level 2 process |  |  | Process
P900 | Level 2 process | 1,2,3,4 |  | Process
1 | Level 3 process |  |  | Process
2 | Level 3 process |  |  | Process
3 | Level 3 process |  |  | Process
4 | Level 3 process |  |  | Process

## WBS-Tall
Employee ID | Name | Title | Manager ID | Role Type
ID1 | Bianca Toscano | Director |  | Executive
ID2 | Aasa Andrejev | Manager, Marketing | ID1 | Manager
ID3 | Paul Lohmus | Manager, Products | ID1 | Manager
ID4 | Sergio Udinese | PR Coordinator | ID2 | Staff
ID5 | Mattia Sabbatini | Content Strategist | ID2 | Consultant
ID6 | Mai Aare | Engineering Lead | ID3 | Staff
ID7 | Aet Kangro | Design Lead | ID3 | Staff
ID8 | Aili Mihhailov | PR Specialist | ID4 | Consultant
ID9 | Lemme Kangur | PR Assistant | ID4 | Assistant
ID10 | Alice Cattaneo | Copywriter | ID5 | Consultant
ID11 | Helbe Piip | Software Engineer | ID6 | Staff
ID12 | Riccardo Buccho | Intern | ID6 | Assistant
ID13 | Jana Piip | UX Designer | ID7 | Staff
ID14 | name | title | ID13 | Staff
ID15 | name | title | ID13 | Staff
ID16 | name | title | ID13 | Staff
ID17 | name | title | ID13 | Staff
ID18 | name | title | ID13 | Staff
ID19 | name | title | ID13 | Staff
ID20 | name | title | ID13 | Staff
ID21 | name | title | ID1 | Staff
ID22 | name | title | ID1 | Staff
ID23 | name | title | ID1 | Staff
ID24 | name | title | ID2 | Staff
ID25 | name | title | ID2 | Staff
ID26 | name | title | ID2 | Staff
ID27 | name | title | ID2 | Staff
ID28 | name | title | ID15 | Staff
ID29 | name | title | ID15 | Staff
ID30 | name | title | ID15 | Staff
ID31 | name | title | ID15 | Staff

## Education
Name | Notes | Link
Data validation with Excel tables |  | https://www.youtube.com/watch?v=OosMHxiaVE8&list=PLG9A6ovzPqX4uTMILULzW_MASdnH8j_1z&index=17&t=28s