## Tasks
Settings | [11 empty] | Dependency Columns | [5 empty] | Actual Work Columns
[12 empty] | (Click the +/- button above to expand/collapse the columns.) | [5 empty] | (Click the +/- button above to expand/collapse the columns.)
Don't do anything with Next ID. It's needed for calculations below. |  | You can add/change statuses if desired. It may impact some color coding in the sheet below. |  | Add names of people you want to assign tasks to. |  | You can add/change/remove Task Groups. |  | These holidays will not be counted as work days in the sheet below. (I'm still working on trying to make this dynamic.) Enter new dates over old ones to update.
Next ID |  | Status |  | Assignee |  | TaskGroup |  | Holidays |  | Potential updates
8 |  | Not Started |  | me |  | Ob1 - Objective 1 |  | 2023-03-05 |  | indicate milestones
|  | In Progress - On Track |  |  |  | Ob2 - Objective 2 |  | 2023-03-06
|  | In Progress - At Risk |  |  |  | Ob3 - Objective 3 |  | 2023-03-07
|  | Blocked |  |  |  | Project |  | 2023-03-08
|  | Completed |  |  |  | Paper |  | 2023-03-09
[6 empty] | Presentation |  | 2023-03-10
[6 empty] | Forward Example |  | 2023-03-11
[6 empty] | Backward Example |  | 2023-03-12
2023-05-29
2023-06-19
2023-07-04
2023-07-24
2023-09-04
2023-10-08
2023-10-09
2023-10-10
2023-10-11
2023-10-12
2023-10-13
2023-10-14
2023-10-15
2023-11-23
2023-11-24
2023-11-25
2023-11-26
2023-12-24
2023-12-25
2024-01-01
2024-01-15
2024-02-19
2024-03-03
2024-03-04
2024-03-05
2024-03-06
2024-03-07
2024-03-08
2024-03-09
2024-03-10
2024-05-27
2024-06-19
2024-07-04
2024-07-24
(Click the +/- button on the left to expand/collapse the settings rows.) | [11 empty] | Assign depedencies between tasks. | [5 empty] | Track actual work on the same sheet if desired.
Instructions
1 | Add a new task by typing in the Task Short Description cell at the bottom of the list.
2 | Click in the ID column to add a task id. (The task ids are needed if you're going to link tasks together. Sorry, I couldn't make this step automatic.)
3 | You can add notes to a task in the Task Notes column. I would NOT recommend using Wrap Text with the notes. It will change the row formatting. If you have a lot of notes in a cell, I suggest expanding the size of the formula pane above instead of trying to read them directly in the spreadsheet.
4 | The sheet is set up to plan up to a year ahead and up to 1000 tasks. (It can be modified to handle more of both.)
5 | Grey columns are calculated, so don't touch the formulas in those columns.
6 | Cells with a red mark in the corner show additional instructions if you hover over them.
(Click the +/- button on the left to expand/collapse the instructions rows.)
Planned start: |  | 2023-02-15 | Today:
Planned end: |  | 2023-03-22 | Planned work:
Planned work days: |  | 21 | Actual work:
Planned calendar days: |  | 35
 | time axis 2023-02-15 to 2024-03-20
ID | Task Short Description | Task Notes | Task Group | Assignee | Status | Percent Complete | Independent Start Date | Independent End Date | Dependency ID | Dependency Type | Dependency Lag Days | Planned Workdays | Planned Start | Planned End | Actual Start | Actual End | Actual Workdays | time axis 2023-02-15 to 2024-03-20
1 | Forward one |  | Forward Example |  |  |  | 2023-03-07 |  |  | FS |  | 2 | 2023-03-07 | 2023-03-13
2 | Forward two |  | Forward Example | [5 empty] | 1 | FS |  | 3 | 2023-03-14 | 2023-03-16
3 | Forward three |  | Forward Example | [5 empty] | 2 | FS |  | 4 | 2023-03-17 | 2023-03-22
4 | Backward one |  | Backward Example |  |  |  |  | 2023-03-07 |  |  |  | 2 | 2023-03-03 | 2023-03-07
5 | Backward two |  | Backward Example | [5 empty] | 4 | SF |  | 3 | 2023-02-28 | 2023-03-02
6 | Backward three |  | Backward Example | [5 empty] | 5 | SF |  | 4 | 2023-02-22 | 2023-02-27
7 | Backward four |  | Backward Example | [5 empty] | 6 | SF |  | 5 | 2023-02-15 | 2023-02-21
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
FS
Formulas:
Status = IF(AND(O73<>"",P73<>""),MAX(P73:P1054),[Status, row above]+1)
Status = NETWORKDAYS(D65,[Status, row above],HolidaysTable[Holidays])
Note on L72: Christopher Macintosh: There are four dependency types available. The first letter in the dependency type codes refers to the other task. The second letter refers to this task. Available Dependency Types: FS - Finish-to-Start (Forward) [Other task finishes before this task starts.] SS - Start-to-Start (Forward) [Both tasks start at the same time.] SF - Start-to-Finish (Backward) [Other task starts after this task finishes.] FF - Finish-to-Finish (Backward) [Both tasks finish at the same time.]
Note on M72: Christopher Macintosh: The dependency lag allows you change the start time of the next task. Positive numbers will push the start date further into the future. Negative numbers will move the start date in the opposite direction. Example: 1 - delays the start date by one day -1 - moves the start day one day sooner

## ProgressReports
Section 1
(Click the +/- button on the left to expand/collapse the section rows.)
Section 2
(Click the +/- button on the left to expand/collapse the section rows.)
Section 3
(Click the +/- button on the left to expand/collapse the section rows.)

## People
Name
John Doe
Jane Noname

## Videos
Gantt Chart (graph) | https://www.youtube.com/watch?v=HfAOkXt5V_8
Gantt Chart (cells) | https://www.youtube.com/watch?v=tuQpGzL_14g
Gantt Chart (cells & dependency) | https://www.youtube.com/watch?v=OizqFlMtZLQ