## WBS-List
Steps to create a Work Breakdown Structure List and Diagram
Step 1: | List your deliverables in separate cells in Row 13 in the Project section starting in column A. Insert more columns after the last deliverable if you need more space.
Step 2: | List the tasks that need to be completed under each deliverable.
Step 3: | Increase the indent on tasks and subtasks. (It makes the lists easier to read.)
Step 4: | Copy the lists of Deliverables and Tasks and paste them in the name column. (You want to create a single column that lists all the deliverables and tasks.)
Step 5: | Give each Deliverable and Task a unique ID number
Step 6: | Label each Deliverable, Task, and Subtask with the correct type in the type column.
Step 7: | Indicate which deliverables belong to the project, which tasks belong to which deliverable, and which subtasks belong to which task by providing the correct ID for each in the dependent column. See the example below.
Step 8: | Copy the information in the 5 columns in the Task List section WITHOUT THE HEADERS and paste it into the table on the left side of the WBS-Chart sheet. (DON'T PASTE OVER THE HEADERS IN THAT SHEET. THE CHART WON'T WORK IF YOU DO.)
Step 9: | Click Refresh in the top-left corner of the chart. You should see a WBS diagram for your project.
Project |  |  | Task List
Deliverable 1 | Deliverable 2 | Deliverable 3 | id | name | type | dependent | blank
Task 1 | Task 4 | Task 7 | 0 | Project | Project
Task 2 | Subtask 4.1 | Task 8 | 1 | Deliverable 1 | Deliverable | 0
Subtask 2.1 | Subtask 4.2 | Task 9 | 2 | Task 1 | Task | 1
Subtask 2.2 | Subtask 4.3 |  | 3 | Task 2 | Task | 1
Subtask 2.3 | Task 5 |  | 4 | Subtask 2.1 | Subtask | 3
Task 3 | Task 6 |  | 5 | Subtask 2.2 | Subtask | 3
|  |  | 6 | Subtask 2.3 | Subtask | 3
|  |  | 7 | Task 3 | Task | 1
|  |  | 8 | Deliverable 2 | Deliverable | 0
|  |  | 9 | Task 4 | Task | 8
|  |  | 10 | Subtask 4.1 | Subtask | 9
|  |  | 11 | Subtask 4.2 | Subtask | 9
|  |  | 12 | Subtask 4.3 | Subtask | 9
|  |  | 13 | Task 5 | Task | 8
|  |  | 14 | Task 6 | Task | 8
|  |  | 15 | Deliverable 3 | Deliverable | 0
|  |  | 16 | Task 7 | Task | 15
|  |  | 17 | Task 8 | Task | 15
|  |  | 18 | Task 9 | Task | 15

## WBS-Diagram
Employee ID | Name | Title | Manager ID | Role Type | Some Visio diagrams are available for use in Excel. They can be added by going to Insert - Get Add-ins - Search for "Visio" - Click Add next to Microsoft Visio Data Visualizer
0 | Project | Project |  |  | Once you've added the Visio Add-in, you can add a chart in a new blank sheet by going to Insert - My Add-ins - Microsoft Visio Data Visualizer - Select the chart you want - Click Create
1 | Deliverable 1 | Deliverable | 0 |  | A chart and data table will be added to the blank sheet. Paste the data needed into the data table. (DON'T PASTE OVER THE TABLE HEADERS. THE CHART WON'T WORK IF YOU DO.)
2 | Task 1 | Task | 1 |  | If you run into problems, create a new blank sheet and start fresh. Get help if you can't figure it out.
3 | Task 2 | Task | 1 |  | You can't edit any aspects of the chart except the underlying data unless you have a Microsoft Visio license.
4 | Subtask 2.1 | Subtask | 3
5 | Subtask 2.2 | Subtask | 3
6 | Subtask 2.3 | Subtask | 3
7 | Task 3 | Task | 1
8 | Deliverable 2 | Deliverable | 0
9 | Task 4 | Task | 8
10 | Subtask 4.1 | Subtask | 9
11 | Subtask 4.2 | Subtask | 9
12 | Subtask 4.3 | Subtask | 9
13 | Task 5 | Task | 8
14 | Task 6 | Task | 8
15 | Deliverable 3 | Deliverable | 0
16 | Task 7 | Task | 15
17 | Task 8 | Task | 15
18 | Task 9 | Task | 15

## TasksGantt
Project Summary Information
Overall start date: |  | 2023-02-21 | Overall task count: |  | 11 | Filtered task count: |  | 11
Overall end date: |  | 2023-03-30 | Completed task count: |  | 3 | Filtered completed task count: |  | 3
Filtered start date: |  | 2023-02-21 | Incomplete task count: |  | 8 | Filtered incomplete task count: |  | 8
Filtered end date: |  | 2023-03-30
Overall work days: |  | 23 | Overall beginning task work days: |  | 26 | Overall remaining task workdays: |  | 14.35
Overall calendar days: |  | 38
Filtered work days: |  | 23 | Filtered beginning task work days: |  | 26 | Filtered remaining task work days: |  | 15.35
Filtered calendar days: |  | 38
Today:
Planned work:
Actual work:
Next ID #: |  | 12
Date: | time axis 2023-02-21 to 2024-03-26
ID | Task Short Description | Task Notes | Task Group | Assignee | Due Date | Status | Percent Complete | Independent Start Date | Independent End Date | Dependency ID | Dependency Type | Dependency Lag Days | Planned Workdays | Planned Remaining | Planned Start | Planned End | Actual Start | Actual End | Actual Workdays | time axis 2023-02-21 to 2024-03-26
1 | Forward one | Start from the beginning of the project. | Forward Example |  |  | Completed | 100% | 2023-03-19 |  |  |  |  | 2 | 0 | 2023-03-19 | 2023-03-20
2 | Forward two |  | Forward Example |  | 2023-03-23 | In Progress - At Risk | 30% |  |  | 1 | FS | 1 | 3 | 2.1 | 2023-03-22 | 2023-03-24
3 | Forward three |  | Forward Example |  |  | Not Started |  |  |  | 2 | FS |  | 4 | 4 | 2023-03-27 | 2023-03-30
4 | Backward one | Start from the end of the project. | Backward Example |  |  | Not Started |  |  | 2023-03-19 |  |  |  | 2 | 2 | 2023-03-17 | 2023-03-19
5 | Backward two |  | Backward Example |  |  | Not Started |  |  |  | 4 | SF |  | 3 | 3 | 2023-03-14 | 2023-03-16
6 | Backward three |  | Backward Example |  |  | Blocked | 50% |  |  | 5 | SF |  | 4 | 2 | 2023-03-01 | 2023-03-13
7 | Backward four |  | Backward Example |  |  | Completed | 100% |  |  | 6 | SF | -1 | 5 | 0 | 2023-02-21 | 2023-02-27 | 2023-02-23 | 2023-03-01 | 5
8 | test1 |  | Paper |  |  | Completed | 100% | 2023-03-19 |  |  |  |  | 1 | 0 | 2023-03-19 | 2023-03-19
9 | test2 |  | Paper |  |  | In Progress - On Track | 75% |  |  | 8 |  |  | 1 | 0.25 | 2023-03-20 | 2023-03-20
10 | test3 |  | Paper |  |  | Not Started |  |  |  | 9 |  |  | 1 | 1 | 2023-03-21 | 2023-03-21
11 | test4 | [8 empty] | 10 |  |  |  | 1 | 2023-03-22 | 2023-03-22
Note on M19: Christopher Macintosh: There are four dependency types available. The first letter in the dependency type codes refers to the other task. The second letter refers to this task. Available Dependency Types: FS - Finish-to-Start (Forward) [Other task finishes before this task starts.] SS - Start-to-Start (Forward) [Both tasks start at the same time.] SF - Start-to-Finish (Backward) [Other task starts after this task finishes.] FF - Finish-to-Finish (Backward) [Both tasks finish at the same time.]
Note on N19: Christopher Macintosh: The dependency lag allows you change the start time of the next task. Positive numbers will push the start date further into the future. Negative numbers will move the start date in the opposite direction. Example: 1 - delays the start date by one day -1 - moves the start day one day sooner

## TasksSummary
Project Phases | Count | Start | End | % Complete | Days Left
Backward Example | 4 | 2023-02-21 | 2023-03-19 | 75% | 7
Backward four | 1 | 2023-02-21 | 2023-02-27 | 100% | 0
Backward three | 1 | 2023-03-01 | 2023-03-13 | 50% | 2
Backward two | 1 | 2023-03-14 | 2023-03-16 |  | 3
Backward one | 1 | 2023-03-17 | 2023-03-19 |  | 2
Forward Example | 3 | 2023-03-19 | 2023-03-30 | 65% | 6.1
Forward one | 1 | 2023-03-19 | 2023-03-20 | 100% | 0
Forward two | 1 | 2023-03-22 | 2023-03-24 | 30% | 2.1
Forward three | 1 | 2023-03-27 | 2023-03-30 |  | 4
Paper | 3 | 2023-03-19 | 2023-03-21 | 87.5% | 1.25
test1 | 1 | 2023-03-19 | 2023-03-19 | 100% | 0
test2 | 1 | 2023-03-20 | 2023-03-20 | 75% | 0.25
test3 | 1 | 2023-03-21 | 2023-03-21 |  | 1
Grand Total | 10 | 2023-02-21 | 2023-03-30 | 75.83% | 14.35

## Settings
NextID | Status | Assignee | TaskGroup | Holidays
12 | Not Started | me | Ob1 - Objective 1 | 2023-03-05
| In Progress - On Track |  | Ob2 - Objective 2 | 2023-03-06
| In Progress - At Risk |  | Ob3 - Objective 3 | 2023-03-07
| Blocked |  | Project | 2023-03-08
| Completed |  | Paper | 2023-03-09
|  |  | Presentation | 2023-03-10
|  |  | Forward Example | 2023-03-11
|  |  | Backward Example | 2023-03-12
2023-05-29
2023-06-19
2023-07-04
2023-07-24
2023-09-04
2023-10-08
2023-10-09
2023-10-10
2023-10-11
2023-10-12
2023-10-13
2023-10-14
2023-10-15
2023-11-23
2023-11-24
2023-11-25
2023-11-26
2023-12-24
2023-12-25
2024-01-01
2024-01-15
2024-02-19
2024-03-03
2024-03-04
2024-03-05
2024-03-06
2024-03-07
2024-03-08
2024-03-09
2024-03-10
2024-05-27
2024-06-19
2024-07-04
2024-07-24