## WBS_List
Steps to create a Work Breakdown Structure List and Diagram
Step 1: | List your deliverables in separate cells in Row 13 in the Project section starting in column A. Insert more columns after the last deliverable if you need more space.
Step 2: | List the tasks that need to be completed under each deliverable.
Step 3: | Increase the indent on tasks and subtasks. (It makes the lists easier to read.)
Step 4: | Copy the project name to the name column of row 0.
Step 5: | Copy the lists of Deliverables and Tasks and paste them in the name column under id 0 (the project name) in the Task List section. (You want to create a single column that lists all the deliverables and tasks.)
Step 6: | Give each Deliverable and Task a unique ID number.
Step 7: | Label each Deliverable, Task, and Subtask with the correct type in the type column.
Step 8: | Indicate which deliverables belong to the project, which tasks belong to which deliverable, and which subtasks belong to which task by providing the correct ID for each in the dependent column. See the example below.
Step 9: | Copy the information in the 5 columns of the Task List section WITHOUT THE HEADERS and paste it into the table on the left side of the WBS-Chart sheet. (DON'T PASTE OVER THE HEADERS IN THAT SHEET. THE CHART WON'T WORK IF YOU DO.)
Step 10: | Click Refresh in the top-left corner of the chart. You should see a WBS diagram for your project.
Project Name |  |  |  | Task List
Deliverable #1 | Deliverable #2 | Deliverable #3 | Deliverable #4 | id | name | type | dependent | blank
Task 1 | Task 5 | Task 8 | Task 18 | 0 | Project Name | Project
Task 2 | Task 6 | Task 9 | Subtask 7 | 1 | Deliverable #1 | Deliverable | 0
Task 3 | Task 7 | Task 10 | Task 19 | 2 | Task 1 | Task | 1
Subtask 1 |  | Task 11 |  | 3 | Task 2 | Task | 1
Subtask 2 |  | Task 12 |  | 4 | Task 3 | Task | 1
Subtask 3 |  | Task 13 |  | 5 | Subtask 1 | Subtask | 4
Task 4 |  | Task 14 |  | 6 | Subtask 2 | Subtask | 4
Subtask 4 |  | Task 15 |  | 7 | Subtask 3 | Subtask | 4
Subtask 5 |  | Task 16 |  | 8 | Task 4 | Task | 1
Subtask 6 |  | Task 17 |  | 9 | Subtask 4 | Subtask | 8
|  |  |  | 10 | Subtask 5 | Subtask | 8
|  |  |  | 11 | Subtask 6 | Subtask | 8
|  |  |  | 12 | Deliverable #2 | Deliverable | 0
|  |  |  | 13 | Task 5 | Task | 12
|  |  |  | 14 | Task 6 | Task | 12
|  |  |  | 15 | Task 7 | Task | 12
|  |  |  | 16 | Deliverable #3 | Deliverable | 0
|  |  |  | 17 | Task 8 | Task | 16
|  |  |  | 18 | Task 9 | Task | 16
|  |  |  | 19 | Task 10 | Task | 16
|  |  |  | 20 | Task 11 | Task | 16
|  |  |  | 21 | Task 12 | Task | 16
|  |  |  | 22 | Task 13 | Task | 16
|  |  |  | 23 | Task 14 | Task | 16
|  |  |  | 24 | Task 15 | Task | 16
|  |  |  | 25 | Task 16 | Task | 16
|  |  |  | 26 | Task 17 | Task | 16
|  |  |  | 27 | Deliverable #4 | Deliverable | 0
|  |  |  | 28 | Task 18 | Task | 27
|  |  |  | 29 | Subtask 7 |  | 28
|  |  |  | 30 | Task 19 | Task | 27
31
32
33
34
35
36
37
38

## WBS_Diagram
Employee ID | Name | Title | Manager ID | Role Type
0 | Project Name | Project
1 | Deliverable #1 | Deliverable | 0
2 | Task 1 | Task | 1
3 | Task 2 | Task | 1
4 | Task 3 | Task | 1
5 | Subtask 1 | Subtask | 4
6 | Subtask 2 | Subtask | 4
7 | Subtask 3 | Subtask | 4
8 | Task 4 | Task | 1
9 | Subtask 4 | Subtask | 8
10 | Subtask 5 | Subtask | 8
11 | Subtask 6 | Subtask | 8
12 | Deliverable #2 | Deliverable | 0
13 | Task 5 | Task | 12
14 | Task 6 | Task | 12
15 | Task 7 | Task | 12
16 | Deliverable #3 | Deliverable | 0
17 | Task 8 | Task | 16
18 | Task 9 | Task | 16
19 | Task 10 | Task | 16
20 | Task 11 | Task | 16
21 | Task 12 | Task | 16
22 | Task 13 | Task | 16
23 | Task 14 | Task | 16
24 | Task 15 | Task | 16
25 | Task 16 | Task | 16
26 | Task 17 | Task | 16
27 | Deliverable #4 | Deliverable | 0
28 | Task 18 | Task | 27
29 | Subtask 7 |  | 28
30 | Task 19 | Task | 27

## TaskList_GanttChart
Project Summary Information
Overall start date: |  | 2023-06-29 | Overall task count: |  | 9 | Filtered task count: |  | 9
Overall end date: |  | 2023-07-21 | Completed task count: |  | 4 | Filtered completed task count: |  | 4
Filtered start date: |  | 2023-06-29 | Incomplete task count: |  | 5 | Filtered incomplete task count: |  | 5
Filtered end date: |  | 2023-07-21
Overall work days: |  | 16 | Overall beginning task work days: |  | 24 | Overall remaining task work days: |  | 11.5
Overall calendar days: |  | 23
Filtered work days: |  | 16 | Filtered beginning task work days: |  | 24 | Filtered remaining task work days: |  | 11.5
Filtered calendar days: |  | 23
Today:
Planned work:
Actual work:
Next ID #: |  | 10
 | time axis 2023-06-29 to 2025-06-28
ID | Description | Notes | Group | Assignee | Due Date | Status | % Complete | Ind Start | Ind End | Dep ID | Dep Type | Lag Days | Plan Days | Plan Remain | Plan Start | Plan End | Actual Start | Actual End | Actual Days | time axis 2023-06-29 to 2025-06-28
1 | Forward one | Start from the beginning | Forward Example | me |  | In Progress - On Track | 25% | 2023-07-12 |  |  |  |  | 2 | 1.5 | 2023-07-12 | 2023-07-13
2 | Forward two |  | Forward Example |  |  | Not Started |  |  |  | 1 | FS |  | 2 | 2 | 2023-07-14 | 2023-07-17
3 | Forward three |  | Forward Example |  |  | Not Started |  |  |  | 2 |  |  | 3 | 3 | 2023-07-18 | 2023-07-20
4 | Forward four |  | Forward Example |  |  | Not Started |  |  |  | 2 |  |  | 4 | 4 | 2023-07-18 | 2023-07-21
5 | Backward one |  | Backward Example |  |  | Blocked | 50% |  | 2023-07-12 |  |  |  | 2 | 1 | 2023-07-11 | 2023-07-12
6 | Backward two |  | Backward Example |  |  | Completed | 100% |  |  | 5 | SF |  | 3 | 0 | 2023-07-06 | 2023-07-10
7 | Backward three |  | Backward Example |  |  | Completed | 100% |  |  | 6 | SF |  | 4 | 0 | 2023-06-29 | 2023-07-05
8 | Backward four |  | Backward Example |  |  | Completed | 100% |  |  | 6 | SF |  | 1 | 0 | 2023-07-05 | 2023-07-05
9 | Backward five |  | Backward Example |  |  | Completed | 100% |  |  | 8 | SF |  | 3 | 0 | 2023-06-29 | 2023-07-03
Note on M19: There are four dependency types available. The first letter in the dependency type codes refers to the other task. The second letter refers to this task. Available Dependency Types: FS - Finish-to-Start (Forward) [Other task finishes before this task starts.] SS - Start-to-Start (Forward) [Both tasks start at the same time.] SF - Start-to-Finish (Backward) [Other task starts after this task finishes.] FF - Finish-to-Finish (Backward) [Both tasks finish at the same time.]
Note on N19: The dependency lag allows you change the start time of the next task. Positive numbers will push the start date further into the future. Negative numbers will move the start date in the opposite direction. Example: 1 - delays the start date by one day -1 - moves the start day one day sooner

## Settings
NextID | Status | Assignee | TaskGroup | Holidays
| Not Started | me | Forward Example | 2023-03-05
| In Progress - On Track |  | Backward Example | 2023-03-06
| In Progress - At Risk |  |  | 2023-03-07
| Blocked |  |  | 2023-03-08
| Completed |  |  | 2023-03-09
2023-03-10
2023-03-11
2023-03-12
2023-05-29
2023-06-19
2023-07-04
2023-07-24
2023-09-04
2023-10-08
2023-10-09
2023-10-10
2023-10-11
2023-10-12
2023-10-13
2023-10-14
2023-10-15
2023-11-23
2023-11-24
2023-11-25
2023-11-26
2023-12-24
2023-12-25
2024-01-01
2024-01-15
2024-02-19
2024-03-03
2024-03-04
2024-03-05
2024-03-06
2024-03-07
2024-03-08
2024-03-09
2024-03-10
2024-05-27
2024-06-19
2024-07-04
2024-07-24